## Sheet1
QUESTION | SELECTION
According to Scrum guidelines, who is responsible for hiring or assigning a new person into a Team? | This is outside of the scope of Scrum.
After a Team has committed to a Sprint goal, what authority does it have? | The Team does whatever is necessary to achieve the goal.
During a Daily Scrum meeting, Olivia mentions she has found an available solution and she thinks that will solve one of the problems she has been working on. She wants to implement it immediately. What is the best next step? | After the Daily Scrum a separate meeting is conducted to discuss the proposed solution.
During a Sprint planning meeting, the Product Owner… | presents stories he/she would like the Team to complete during the Sprint.
How are development Teams guided during a Sprint? | By their collective knowledge and experience.
If a Development Team determines that it has over-committed itself for a Sprint, who should be present when reviewing and adjusting the Sprint goal and work? | Product Owner, ScrumMaster and Development Team.
In Scrum, what does a team attempt to produce every Sprint? | A potentially shippable product increment.
What are the desirable qualities of a Product Vision? | Describes why the project is pursued and the product desired end state.
What is the main purpose of a Sprint Review? | For the Scrum Team and stakeholders to review what the Scrum Team has built, and to collaborate on what could be done next to create value.
When should the Release Burndown Chart be updated? | After every Sprint
Which of the following BEST represents the Product Owner's responsibility? | Optimizing the business value of the work.
Which technique might a ScrumMaster use to facilitate communication between the development Team and Product Owner? | All of there
Who is primarily responsible for facilitation, when required, in Scrum meetings? | ScrumMaster
Why should the Product Owner attend the Daily Scrum? | To help clarify requirements.
What is MOST likely to result if the Product Owner is not available during a Sprint? | The product increment may not meet expectations.